## Phase-1_3.0
Phase I
Id | Module | Platform | Detailed Requirements (Flow) | Deadline |  | Owner | Dependency | Comments | Reason for delay | Status
1 | Catalogue Management (Contd.) | Web | Catalogue items can be prioritized in each of the catalogue | 2 Working Days | Sweet Valentines Day (Wenesday) February 15th (Thursday) | Junaid | No | None | No delay | Completed
2 | Catalogue from and to | Web | Catalogue can remain active till date decided | 1 Working Day | February 16th (Friday) | Junaid | No | None | No delay | Completed
3 | Invoice number on order | Web | Invoice number should be generated on every order | Same Day | Same Day | Junaid | No | None | No delay | Completed
4 | Order History (Web Service) | Mobile | Order history of employee signed in | Same Day | Same Day | Junaid | No | None | No delay | Completed
5 | Employee Details (Web Service) | Mobile | Details of employee signed in | Same Day | Same Day | Faizan | Junaid | None | No delay | Completed
7 | Attendance on base station | Web/Mobile | Attendance on day start and day end on a exact latitude/longitudes marked as base station by Web Admin | 2 Working Days depends on testing | February 19th (Monday) February 20th (Tuesday) | Faizan | Junaid | None | No delay | Completed
8 | Retailer Types | Web | There should be multiple retailer types | 1/2 Working day | February 21st (Wednesday) | Junaid | No | None | No delay | Completed
9 | Retailer territory | Web | There should be territory in which a retailer resides. Area is marked right now. | Same Day | Same Day | Junaid | No | None | No delay | Completed
10 | Campaign Management | Web | Campaigns are created Retailer wise. For example: Retailer A is given a certain offer on individual inventory items. So when booker goes to a retailer, he will also be shown campaign for that particular retailer automatically, if available. Note: Complete & Comprehensive document required | 4-5 Working Days | February 22nd (Thursday) February 23rd (Friday) February 26th (Monday) February 27th (Tuesday) February 28th (Wednesday) | Junaid | No
Phase II
11 | KPI Management | Web | Basic KPI management which allocates KPI based on direct reporting. This KPI also includes Inventory Wise KPI and not just textual KPI. Scores will automatically be calculated instead of giving manual scores. Note: A detailed document is required when developing this feature | Based on the complete document | Based on the complete document | Junaid | No | N/A | N/A | N/A
12 | Retailer Payment Credit Terms | Web | A very detailed document is required which will also allow me to understand the basics on Credits. This feature will allow Retailers to acquire inventory on credit and they can also make partial payments instead of complete payments. Deadlines will also be assigned to retailers individually based on the Credit Amount. Deadline can also be extended based on partial payment amount. Note: This is the knowledge which I acquired after having a little chat on Credit terms with Waqas Bhai. So only complete document enables me to provide deadlines on this particular feature | Based on the complete document | Based on the complete document | Junaid | No | N/A | N/A | N/A