## Sheet1
WEB MODULES
S.No | Feature | Sub Modules | Description | Status Design/Functionality | Testing
1 | Employee Management | Add Employee - Update Employee - Delete Employee | Employee can be added/updated/deleted at any time | Completed/Completed | Pending
2 | Region Management | Add Region - Update Region - Delete Region | Region can be added/updated/deleted at any time. Regions are also assigned a POC from existing employees | Completed/Completed | Pending
3 | Area Management | Add Area - Update Area - Delete Area | Area can be added/updated/deleted at any time. Areas are also assigned a POC from existing employees | Completed/Completed | Pending
4 | Territory Management | Add Territory - Update Territory - Delete Territory | Territory can be added/updated/deleted at any time. Territories are also assigned a POC from existing employees | Completed/Completed | Pending
5 | Inventory Management | Add Inventory - Update Inventory - Delete Inventory | Inventory can be added/updated/deleted at any time. Each item is fullfilling all the inventory requirements which were sent to me before Inventory Restructure | Completed/Completed | Pending
6 | Sub-Inventory Management | Add Sub-Inventory - Update Sub-Inventory - Delete Sub-Invenotry | Sub Inventory is the inventory which reflects a parent item and a child item. It also reflects quantity of a child in its parent. System also has the ability to convert child into it's native unit and complete parent will be converted into child | Completed/Completed | Pending
7 | Packaging Management | Add Packaging - Update Packaging - Delete Packaging | Packaging reflects inventory variants in which an items arrives at the warehouse. For instance, Dairy Milk comes in Pieces, Boxes and Cartans. So Piece, Box and Cartan are Inventory Variants | Completed/Completed | Pending
8 | Catalogue Management | Creat Catalogue - Update Catalogue - Delete Catalogue | Catalogue is basically a group of Inventory items. Each catalogue reflects number of inventory items | Completed/Completed | Pending
9 | Catalogue Assignments | Assign Catalogue - Update Assignment - Delete Assignment | Each catalogue can be assigned to an employee. Each employee can only be assigned a single catalogue at given time. The Catalogue will then be visible to employee thorugh mobile | Completed/Completed | Pending
10 | Distributors Management | Add Distritbutor - Update Distributor - Delete Distributor | Distributors can be added/updated/deleted at any time. | Completed/Completed | Pending
11 | Distributor Type Management | Add Distributor Type - Update Distributor Type - Delete Distributor Type | Distributors will have a type which can also be given a certain discount | Completed/Completed | Pending
12 | Distributors Assignment | Add Assignment - Update Assignment - Delete Assignment | Distributors are assigned to each employee through web. Only those distributors which are assigned to a particular employee will reflect in the app | Completed/Completed | Pending
13 | Orders Management | Update Order Items - Process Order - Complete Order - Cancel Order | Admin can view/update any order. Admin can update quantity of the items booked by the booker and the price will automatically be updated. Admin can also expand the order in which one can add booker discount too | Partially Completed/Completed | Pending
14 | Categories Management | Add Main & Sub Category - Update Main & Sub Category - Delete Main & Sub Category | Categories can be assigned to each of the item. All the items can only be accessed through categories from mobile app | Completed/Completed | Pending
15 | Bulletin Messages Management | Create Message - Send Message - Delete Message | Messages can be broadcasted from web to individual employee and also a group of employees | Completed/Completed | Pending
16 | Bulletin Groups Management | Add Bulletin Group - Update Bulletin Group - Delete Bulletin Group | Admin can create groups of employees to whome one wants to send a message altogether | Completed/Completed | Pending
MOBILE SERVICES
S.No | Feature | Description | Status | Testing | Final Ver.
1 | GetAllTerritories | Mobile app can receive | Deployed | Tested | v8.0
2 | GetAllRetailerTypes | All distributor types will be reflected for distributors while adding a retailer on app | Deployed | Tested | v8.0
3 | AddRetailer | App can add a retailer | Deployed | Tested | v8.0
4 | GetAllRetailers | App can view all the distributors | Deployed | Tested | v8.0
5 | UpdateRetailer | App can update a distributor | Deployed | Tested | v8.0
6 | Login | App has a login feature | Deployed | Tested | v8.0
7 | Signout | App has a signout feature | Deployed | Tested | v8.0
8 | GetCatalogue | Service will send a catalogue which is assigned to the employee on current day | Deployed | Tested | v8.0
9 | BookOrder | Order can be booked from the app | Deployed | Tested | v8.0
10 | GetEmployeeProfile | Employee can view the profile at the app | Deployed | Tested | v8.0
11 | GetEmployeeOrders | Employee can view orders history | Deployed | Tested | v8.0
12 | CheckInAttendance | Attendance Management System requires a check in at day start | Deployed | Tested | v8.0
13 | CheckOutAttendance | Attendance Management System requires a check-out at any given time | Deployed | Tested | v8.0
14 | MarkVisit | Employee can mark a distributor as visited after visiting the distributor | Deployed | Tested | v8.0
15 | GetMerchantMarkStatusForToday | Employee can check if a distributor is marked for today or not | Deployed | Tested | v8.0
16 | PlanVisits | Employee can plan a visit to a certain group of distributors or an individual | Deployed | Tested | v8.0
17 | UpdatePlanVisits | Employee can update a planned visit. We do not have an update plan visit screen for now | Deployed | Tested | v8.0
18 | GetPlanVisit | Employee can see distributors from created plan | Deployed | Tested | v8.0
19 | GetBulletin | Employee can see bulletins/messages sent to him/her | Deployed | Tested | v8.0
20 | DoneVisits | Employee can see total visits done in a day | Deployed | Tested | v8.0
21 | GetCategoriesList | Inventory items are populated according to a category | Deployed | Tested | v8.0